## Sheet1
| October 27- Nov 3 | Nov 3 - Nov 10 | Nov 10 - Nov 17 | Nov 17- Nov 24 | Nov 24 - Nov 26/28 | Total time
| Design | Prototypes - Mechanical design must be done, code must be started and we must have working prototypes | Code must be done. Re-evaluation of design | Testing/Tweaking of robots to eliminate bugs and make code reliable and robust | Demo/>Еxtra testing, time permitting
Rana | 5 | 10 | 17 | 12 | 9 | 53
Patrick | 4.5 | 6 | 6 | 28 | 8 | 52.5
Sucong | 5 | 3 | 4 | 12 | 7 | 31
George | 5 | 7 | 8 | 30 | 12 | 62
Kamraan | 5 | 10 | 8 | 18 | 9 | 50
Tony | 4.5 | 15 | 8 | 10 | 14 | 51.5
[5 empty] | Total time: | 300
Status |  |  | Code still in progress, almost done | Code done - testing
|  |  | Mechanical design done | Mechanical design done
|  |  | Switched to RobotC | Putting everyting together on Sunday
Note on B6: Kickoff meeting. Generate basic documentation and Gantt diagram. Evaluated code. --geo.ciobanu November 13, 2008 5:56:38 PM
Note on C6: Generate detailed documentation. Design robots with Patrick. Design Communication code with Rana. Discuss task assignment with everyone. Develope PLAN B. --geo.ciobanu November 13, 2008 5:57:08 PM
Note on D6: Organized team, evaluated RobotC, Organized SVN, Instructed people on it, Ported code to RobotC --geo.ciobanu November 13, 2008 5:55:20 PM
Note on E6: -Finished writing navigation -Helped the other team members migrate to RobotC -Researched and experimented with Bluetooth -Worked with other team members on their parts -Improved the design of the two robots -Wrote the API document -Finalized the high- and low-level design --geo.ciobanu November 19, 2008 2:38:26 PM